## Sheet1
Week | Deploy Application
20/3/2023 | Collect project informations
27/3/2023 | Build CI pipeline
2023-03-04 | Build CD pipeline
2023-10-04 | Deploy to Sandbox Environment
17/04/2023 | Apply Unit tests and Integration tests
24/4/2023 | QA test and collect bugs
2023-01-05 | Fix bugs from QA report
2023-08-05 | Deploy to Staging
15/5/2023 | Test and feedback from local users
22/5/2023 | Fix bugs from feedback if possible
29/5/2023 | Deploy to Production
2023-05-06 | Monitoring Application
Goals
FlaskML API Deployed
Fully CICD pipelines include build, test, deploy