## Sheet1
Week | Deploy Application | Level
20/3/2023 | Collect project informations | Low
27/3/2023 | Build CI pipeline | Medium
2023-03-04 | Build CD pipeline | Medium
2023-10-04 | Deploy to Sandbox Environment | Low
17/04/2023 | Apply Unit tests and Integration tests | Low
24/4/2023 | QA test and collect bugs | Low
2023-01-05 | Fix bugs from QA report | High
2023-08-05 | Deploy to Staging | Medium
15/5/2023 | Test and feedback from local users | Medium
22/5/2023 | Fix bugs from feedback if possible | Medium
29/5/2023 | Deploy to Production | High
2023-05-06 | Monitoring Application | High
| Goals | Level
| FlaskML API Deployed | Medium
Quarter 4 Plan | Design the containerize system for the API | Medium
| Building containerize image using Docker/ Kubernetes | High
Annual Plan | Improve The CI/CD Process | Medium
| Develop new feature for FlaskML API | Medium